SS304L Caustic Soda (NaOH) Storage Tank

Quotation Comparison & Technical Review Report

Project: 2 Nos. SS304L Caustic Soda Tanks (1,600 m³ each) — 91 Sakra Avenue, Jurong Island

Client: CI Manufacturing Pte Ltd / Chemical Industries (Far East) Limited

Date: 8 June 2026

Sources: 3 Quotations · FES Drawings · FES Schedule · FES Presentation (PPTX)

Status: DRAFT FOR CLIENT REVIEW — Confidential

# SS304L Caustic Soda (NaOH) Storage Tank — Quotation Comparison & Technical Review Report

Project: 2 Nos. SS304L Caustic Soda (NaOH) Storage Tanks (1,600 m³ each) — 91 Sakra Avenue, Jurong Island

Client: CI Manufacturing Pte Ltd / Chemical Industries (Far East) Limited

Report Date: 8 June 2026

Sources Reviewed: 3 Quotations, FES Engineering Drawings, FES Project Schedule, FES Technical Presentation (PPTX)

Status: DRAFT FOR CLIENT REVIEW — Confidential

## ⚠️ URGENT PRE-READ: THREE CRITICAL FINDINGS

Before reviewing this report, note the following findings that fundamentally affect the tender evaluation:

FINDING 1 — DIFFERENT TANKS BEING PRICED: The three vendors have designed tanks with completely different geometries. FES: 11,450 mm ID × 15,400 mm H. Credo: 10,000 mm D × 20,500 mm H. Synergex: 10,000 mm D × 23,000 mm H. These are NOT like-for-like quotations. A common design basis must be issued before any award is made.

FINDING 2 — FES TANK IS UNDERSIZED: FES's proposed tank (11,450 mm × 15,400 mm) has a geometric volume of only ~1,585 m³. After applying API 650 mandatory freeboard (minimum 150–600 mm for gas expansion), the working capacity falls to approximately 1,506–1,554 m³ — 94–97% of the required 1,600 m³. This is a design deficiency.

FINDING 3 — ALL BUND WALLS ARE UNDERSIZED: NEA/SCDF regulations require secondary containment of ≥110% of the largest single tank volume (1,760 m³). Engineering calculations show all three proposed bund wall heights are insufficient to achieve this containment given the proposed bund footprints.

## EXECUTIVE SUMMARY

Three quotations have been received and reviewed for the design, fabrication, erection, and civil works for 2 nos. SS304L Caustic Soda (NaOH) Storage Tanks of 1,600 m³ each at 91 Sakra Avenue, Jurong Island.

| Rank | Category | Vendor |
| --- | --- | --- |
| Best Technical Specification | Most detailed API 650 basis | Synergex |
| Best Commercial Terms | Lowest price, most complete scope | Falkor (FES) |
| Lowest Project Risk | Best documentation, schedule, bonding | Falkor (FES) |
| Best Overall Value — RECOMMENDED | Subject to mandatory clarifications | Falkor (FES) |

Recommendation: Award to Falkor Engineering Services (FES) at SGD 2,770,000 subject to resolution of all mandatory clarifications in Section 12. The price advantage is SGD 1,298,000–1,330,000 (47–48%) versus competitors. However, a common Design Basis must first be issued to all vendors to ensure the final tank design achieves 1,600 m³ working capacity with correct freeboard, compliant bund sizing, and all NaOH-service requirements addressed.

## SECTION 1 — FES TECHNICAL PRESENTATION: KEY FINDINGS

The FES PowerPoint presentation (20 slides, dated 4 June 2026) provided critical technical detail absent from the written quotation.

### 1.1 Tank Dimensions (FES Design)

| Parameter | Value from Presentation |
| --- | --- |
| Tank Internal Diameter (ID) | 11,450 mm (11.45 m) |
| Tank Shell Height | 15,400 mm (15.4 m) |
| Nominal Capacity | 1,600 m³ × 2 nos. |
| Bund Wall Height | 2,100 mm (2.1 m) |
| Piling Height above Ground | 1,700 mm (foundation slab to tank bottom) |
| Piles per Tank | 20 (confirmed by 3D model, Slide 4) |
| Piping | SS304L Sch-80 3" × 2 lines × 200m |

### 1.2 Subcontractor Schedule (Slide 2)

| Trade | Appointed Subcontractor |
| --- | --- |
| Mechanical | Falkor Engineering Services Pte Ltd |
| Civil | Falkor Engineering Services Pte Ltd |
| Scaffolding | Falkor Engineering Services Pte Ltd |
| Painting | Falkor Engineering Services Pte Ltd |
| Engineering (PE) | K P Koh & Partners Pte Ltd |
| E&I | Radiant Electrical Pte Ltd (excluded from quote) |
| NDT | SNDT |
| Calibration | SNDT |
| Crane | Denzai |
| Hydrotest Water | PUB |

### 1.3 Construction Methodology (Confirmed from Slides 9–17)

Erection method: Bottom-up (annular plate → bottom plates → shell courses → roof). NOT jacking method.

Welding: Arc welding (SMAW/GMAW) for all plates

Roof type: Fixed cone roof with rafters (confirmed by Slide 16: "Roof Rafters")

NDT stated: PT (Penetrant Testing) — confirmed in Slide 9: "TO DO WELDING AND PT INSPECTION AS PER APPROVED ITP"

PSSR: Pre-Startup Safety Review included (Slide 17)

Work sequence: Hydrotest → Chemical cleaning → Calibration → Punch list → Box-up → MDR → Handover

### 1.4 Critical Observations from Presentation

NDT is PT only — confirmed across multiple slides. No RT or UT mentioned anywhere. This is the most critical technical deficiency.

K P Koh & Partners is the PE firm — reputable Singapore structural/PE consultancy.

SNDT as NDT contractor — unverified accreditation. Must confirm SNDT holds MOM/SAC-SINGLAS accreditation for RT/UT (if upgraded) and PT.

Foundation height 1,700 mm above grade — tank bottom sits 1.7 m above existing ground level. This affects bund wall effective containment height (see Section 7).

20 piles per tank confirmed visually in 3D model — this remains a major engineering concern.

## SECTION 2 — TANK DIMENSION & CAPACITY ANALYSIS

### 2.1 Geometry Comparison Across Three Vendors

| Parameter | FES (Falkor) | Credo | Synergex |
| --- | --- | --- | --- |
| Internal Diameter | 11,450 mm | 10,000 mm | 10,000 mm |
| Shell / Total Height | 15,400 mm | 20,500 mm | 23,000 mm (overall) |
| Geometric Volume | ≈ 1,585 m³ | ≈ 1,610 m³ | ≈ 1,806 m³ |
| Required Working Volume | 1,600 m³ | 1,600 m³ | 1,600 m³ |

Volume calculations:

FES: π/4 × 11.45² × 15.4 = 1,585 m³ ❌ Below 1,600 m³ even at zero freeboard

Credo: π/4 × 10.0² × 20.5 = 1,610 m³ ≈ marginal (before freeboard)

Synergex: π/4 × 10.0² × 23.0 = 1,806 m³ ✅ (accounts for freeboard)

### 2.2 API 650 Freeboard Requirement

API 650 requires the maximum design liquid level to be set below the top of the shell, leaving gas expansion space. Typical minimum freeboard values:

| Freeboard | FES Working Volume | Credo Working Volume | Synergex Working Volume |
| --- | --- | --- | --- |
| 150 mm (min) | 1,570 m³ ❌ | 1,598 m³ ≈ | 1,795 m³ ✅ |
| 300 mm (typical) | 1,554 m³ ❌ | 1,586 m³ ❌ | 1,782 m³ ✅ |
| 600 mm (conservative) | 1,524 m³ ❌ | 1,563 m³ ❌ | 1,759 m³ ✅ |

Conclusion: FES tank cannot achieve 1,600 m³ working capacity at any standard freeboard. Credo is marginal. Only Synergex's 23 m height adequately provides 1,600 m³ working capacity with standard freeboard. This may explain why Synergex chose 23 m height — it is the technically correct approach for this capacity, not an over-design.

For FES to achieve 1,600 m³ at 11,450 mm ID with 300 mm freeboard:

Required total shell height = (1,600 / 102.95) + 0.3 = 15.54 + 0.3 = 15,840 mm minimum

FES currently proposes 15,400 mm — 440 mm too short

🔴 CRITICAL: FES must revise the tank height to at least 15,840 mm (recommend 16,000 mm) to achieve 1,600 m³ working capacity with compliant freeboard. This was not apparent from the written quotation and was only identified from the PPTX.

### 2.3 H/D Ratio Assessment (Structural Stability)

| Vendor | H/D Ratio | Assessment |
| --- | --- | --- |
| FES | 15.4 / 11.45 = 1.35 | Squat, wide tank. Lower wind moment, excellent seismic stability. Wind girder may not be needed. |
| Credo | 20.5 / 10.0 = 2.05 | Tall-to-diameter ratio. Intermediate wind moment. Wind girder likely required. |
| Synergex | 23.0 / 10.0 = 2.30 | Tall, slender tank. Higher wind overturning moment. Wind girder definitely required. |

For API 650 tanks: wind girder is typically required when H/D > 1.5 (per API 650 §5.9). Both Credo and Synergex likely require a top wind girder and possibly an intermediate wind girder — neither vendor has stated this in their scope.

## SECTION 3 — VENDOR COMPARISON TABLE (MASTER)

| Parameter | FALKOR (FES) | CREDO E&C | SYNERGEX |
| --- | --- | --- | --- |
| Quotation Ref | BC-Q3097/CIL/26 | CEC/CIL/011R2/26 | SNG/006/01/26 R1 |
| Date | 4 June 2026 | 3 June 2026 | 29 May 2026 |
| Tank Quantity | 2 nos. | 2 nos. | 2 nos. |
| Nominal Capacity | 1,600 m³ each | 1,600 m³ each | 1,600 m³ each |
| Internal Diameter | 11,450 mm (from PPTX) | 10,000 mm | 10,000 mm |
| Shell Height | 15,400 mm (from PPTX) | 20,500 mm | 23,000 mm (overall) |
| Geometric Volume | 1,585 m³ ❌ | 1,610 m³ (marginal) | 1,806 m³ ✅ |
| Working Volume (300mm freeboard) | 1,554 m³ ❌ | 1,586 m³ ❌ | 1,782 m³ ✅ |
| H/D Ratio | 1.35 (squat) | 2.05 (tall) | 2.30 (tall) |
| Design Code | API 650 (edition not stated) | Not stated | API 650, 13th Ed., Mar 2020 |
| Material — All Plates | A240-304L | SS304 (L-grade not confirmed) | SS304L |
| Shell Course Thicknesses | Not stated | Not stated | Not stated |
| Corrosion Allowance | Not stated | Not stated | Not stated |
| Design Pressure / Vacuum | Not stated | Not stated | Not stated |
| Design Temperature | Not stated | Not stated | Not stated |
| Roof Type | Fixed cone (confirmed from PPTX) | Not stated | Not stated |
| Wind Girder | Not stated (H/D=1.35: borderline) | Not stated (H/D=2.05: required) | Not stated (H/D=2.30: required) |
| Wind Speed Design Basis | Not stated | Not stated | Not stated |
| Seismic Design | Not stated | Not stated | Not stated |
| Bottom Plate Spec | Not stated | Not stated | Not stated |
| Material Weight | Not stated | 82 t/tank | ~88 t/tank |
| Nozzle Schedule | Ref. GA drawings (no detail) | Not stated | Not stated |
| Internal Coating | Not stated | Not stated | Not stated |
| External Coating / Painting | Included (spec not stated) | Not included | Not included |
| Passivation | HF acid cleaning only (not ASTM A380) | Degreasing + passivation (material by CIL) | Degreasing + passivation |
| Caustic SCC Assessment | Not mentioned | Not mentioned | Not mentioned |
| Insulation / Heat Tracing | Excluded | Not stated | Not stated |
| Staircase | Handrails (SS); staircase not explicit | External staircase | Spiral staircase |
| Wind Girder | Not stated | Not stated | Not stated |
| Internal Sump | Not stated | Not stated | Not stated |
| Dip Plate / Anti-vortex | Not stated | Not stated | Not stated |
| Lightning Protection | Not included | Included (SGD 35,000) | Included (SGD 57,200) |
| Overfill Protection (API 2350) | Not stated | Not stated | Not stated |
| Settlement Monitoring | Not stated | Not stated | Not stated |
| Scaffolding | Internal + external ✅ | Included | Included |
| NDT — Shell Welds | PT only ❌ NON-COMPLIANT | UT (no standard) | "UT etc." (vague) |
| NDT — Piping | RT ✅ | Not stated | N/A |
| NDT Contractor | SNDT | Not stated | Not stated |
| Vacuum Box Test | Not mentioned | Not mentioned | Not mentioned |
| Hydrotest | Full water height ✅ | Not mentioned ❌ | Not explicitly stated |
| Piping Pressure Test | Water flush + pressure test ✅ | Not stated | N/A |
| PSSR | Included ✅ | Not mentioned | Not mentioned |
| ITP / QCP | Mentioned ✅ | Not mentioned | Not mentioned |
| MDR / Data Book | Included ✅ | Not mentioned | Not mentioned |
| WPS / PQR | Not mentioned | Not mentioned | Not mentioned |
| Welder Qualification | Not mentioned | Not mentioned | Not mentioned |
| Mill Certificates (MTRs) | Not mentioned | Not mentioned | Not mentioned |
| As-Built Drawings | Not explicit | Survey only | Not stated |
| Tank Calibration | Included (SGD 5,000/tank) ✅ | Not mentioned | Not mentioned |
| Civil — Pile Type | Unknown | Micropile 200mm dia | RC Jack-in 200×200mm |
| Civil — Pile Length | Unknown | 33 m | 12 m |
| Civil — Piles/Tank | 20 | 74 | 125 |
| Civil — Foundation Slab | Not stated | 350 mm RC | 400 mm RC |
| Civil — Bund Wall Height | 2,100 mm (PPTX) | 2,200 mm | 4,000 mm |
| Bund Containment (calc'd) | Insufficient ❌ | Insufficient ❌ | Insufficient ❌ |
| Insurance (CAR/PL) | Not explicit | CAR + PL (SGD 15,000) | Project Insurance |
| Performance Bond | Offered ✅ | Waived ❌ | Not stated |
| Liquidated Damages | Not stated | Explicitly excluded ❌ | Not stated |
| Warranty | Not stated | Not stated | Not stated |
| Authority Submissions | PE + Authority (JTC/BCA implied) | JTC, URA, BCA, SCDF, LTA(VP), NParks, NEA, PUB ✅ | BCA, PE submission |
| Delivery Schedule | 36-week program ✅ | Not provided ❌ | "TBA" ❌ |
| Quotation Validity | 30 days | 30 days | 14 days ❌ |
| Payment Terms | 20% DP, monthly, 30 days | "To be discussed" ❌ | 35 days, milestones |
| GST | Subject to GST | Excluded | Excluded |
| GRAND TOTAL (SGD) | 2,770,000 | 4,068,000 | 4,100,000 |

## SECTION 4 — PRICE BREAKDOWN

### 4.1 Falkor (FES) — SGD 2,770,000

| Section | Item | SGD |
| --- | --- | --- |
| Sec. 1 | Engineering & Authority Submissions | 156,000 |
| Sec. 1 | Civil Works (piling, foundation, bund walls) | 1,020,000 |
|  | Sub-Total Section 1 | 1,176,000 |
| Sec. 2 | Tank No. 01 — Erection Manpower | 113,725 |
|  | Scaffolding (Internal & External) | 15,000 |
|  | Welding Consumables | 77,315 |
|  | Materials (SS plates, fittings, nozzles) | 127,273 |
|  | NDT (PT only) | 11,000 |
|  | CNC Plate Cutting | 6,250 |
|  | Plate Rolling | 35,900 |
|  | Mobile Crane + Lorry Crane + Equipment + Transport | 114,513 |
|  | Tank Survey & Calibration | 5,000 |
|  | Painting | 12,500 |
|  | Hydrostatic Test | 18,750 |
|  | Chemical Cleaning | 12,500 |
|  | Indirect Cost & Site Facilities | 132,500 |
|  | Sub-Total Section 2 (Tank 01) | 682,225 |
| Sec. 3 | Tank No. 02 — identical to Tank 01 | 682,225 |
| Sec. 4 | Piping — Supervision & Labour | 83,349 |
|  | Piping — Consumables & Documentation | 30,900 |
|  | Piping — Materials | 70,300 |
|  | Piping — NDT (RT) | 19,800 |
|  | Piping — Water Flush & Pressure Test | 2,400 |
|  | Piping — Scaffolding | 18,000 |
|  | Piping — Transport & Equipment | 4,800 |
|  | Sub-Total Section 4 (Piping 200m × 2) | 229,549 |
|  | GRAND TOTAL | 2,770,000 |

*Tank steel works only (Sec. 2 + Sec. 3): SGD 1,364,450*

*Civil + Engineering (Sec. 1): SGD 1,176,000*

*Piping (Sec. 4): SGD 229,549*

### 4.2 Credo E&C — SGD 4,068,000

| Item | Description | SGD |
| --- | --- | --- |
| A | Prelims: Insurance, Surveyor, Authority Submissions, RTO | 170,000 |
| B1 | Piling (74 micropiles × 200mm × 33m per tank, incl. load tests) | 850,000 |
| B2 | RC Foundation (350mm slab), Bund Wall, Drain, Sump | 590,000 |
| B3 | Tank Supply & Install × 2 (10m D × 20.5m H, 82t/tank SS304) | 2,350,000 |
| B4 | Lightning Protection (2 tanks) | 35,000 |
| B5 | Scaffold Erection | 55,000 |
| B6 | Degreasing & Passivation (passivation material by CIL) | 70,000 |
| B7 | SS Pipeline NaOH connection | 98,000 |
|  | Goodwill Discount | (150,000) |
|  | GRAND TOTAL | 4,068,000 |

### 4.3 Synergex — SGD 4,100,000

| Item | Description | SGD |
| --- | --- | --- |
| 1 | Tank supply, fab, install × 2 (10m D × 23m H, ~88t/tank SS304L) | 2,744,000 |
| 2 | RC Foundation (400mm slab, 4m bund, 250 RC jack-in piles) | 1,158,600 |
| 3 | Lightning Protection (2 tanks) | 57,200 |
| 5 | Degreasing & Passivation (2 tanks) | 141,000 |
| 6 | BCA/PE Submission, Safety Mgmt, Project Insurance | 282,800 |
|  | Project Discount | (283,600) |
|  | GRAND TOTAL | 4,100,000 |

### 4.4 Comparable Price Summary

| Cost Element | FES | Credo | Synergex |
| --- | --- | --- | --- |
| Tank fabrication & install | 1,364,450 | ~2,308,000* | 2,744,000 |
| Civil (piling + foundation + bund) | 1,020,000 | 1,440,000 | 1,158,600 |
| Engineering & Authority | 156,000 | 170,000 | 282,800 |
| Piping | 229,549 | 98,000 | Not in scope |
| LP + Scaffold + Cleaning | — | 160,000 | 198,200 |
| Grand Total | 2,770,000 | 4,068,000 | 4,100,000 |
| Variance vs FES | Baseline | +SGD 1,298,000 (+47%) | +SGD 1,330,000 (+48%) |

*Credo tank cost estimated by deducting civil, prelims, LP, scaffold, cleaning, piping from total*

## SECTION 5 — NaOH SERVICE REQUIREMENTS & CHEMICAL RISKS

This section covers critical process and chemical engineering requirements specific to Sodium Hydroxide (NaOH) storage. None of these risks are addressed by any vendor.

### 5.1 NaOH Properties Relevant to Tank Design

| Property | Value | Design Implication |
| --- | --- | --- |
| Chemical name | Sodium Hydroxide (Caustic Soda) | Class 8 Corrosive — SCDF/NEA regulated |
| Typical storage concentration | 25–50% w/w | Verify with process team |
| Specific gravity (25% NaOH) | ~1.27 | Foundation load: 1,600 × 1.27 = 2,032 t |
| Specific gravity (48% NaOH) | ~1.50 | Foundation load: 1,600 × 1.50 = 2,400 t |
| Specific gravity (100% NaOH) | 2.13 | Not stored as pure solid in these tanks |
| Freezing point (25% NaOH) | ~−25°C | Not an issue in Singapore |
| Freezing point (50% NaOH) | +12°C | May solidify in cool conditions |
| Flash point | None (non-flammable) | No ATEX requirement for tank |
| UN classification | UN 1824 (solution) | Placarding and containment required |

Action required: Client must confirm NaOH concentration before tank design is finalised. At >48% concentration, the fluid specific gravity increases the foundation loads and may change the material compatibility assessment.

### 5.2 Caustic Stress Corrosion Cracking (SCC) — CRITICAL RISK

This is the single most important material risk for this project. No vendor has addressed it.

Austenitic stainless steels (SS304, SS304L) are susceptible to Caustic Stress Corrosion Cracking (SCC), also called caustic embrittlement, when exposed to NaOH above certain temperature/concentration thresholds.

| NaOH Concentration | Safe Temperature (SS304L) | Risk Level |
| --- | --- | --- |
| < 25% | Up to 60°C | LOW — generally safe |
| 25–50% | Up to 40°C | MODERATE — monitor temperature |
| 25–50% | 40–60°C | HIGH — SCC risk exists |
| > 50% | Any elevated temp | VERY HIGH — SCC highly likely |
| Any | > 80°C | CRITICAL — SS304L unsuitable |

Root cause: High residual weld stresses + NaOH environment + elevated temperature = intergranular cracking. The combination of NaOH penetrating grain boundaries and tensile residual stresses from welding drives crack propagation, often with no visible external corrosion.

Mitigation options:

Confirm NaOH temperature will remain <40°C — the most important action item

If temperature may exceed 40°C: require full PWHT (stress relief at 900°C for 30 min/25mm) — note this conflicts with 304L grade selection (PWHT of 304L can cause sensitisation if done incorrectly)

Alternatively, upgrade material to SS316L or nickel alloy (Alloy 400/Alloy 200) for higher temperature/concentration service

Low delta ferrite weld metal — reducing residual stresses in weld heat-affected zones

Shot peening of weld zones to convert tensile to compressive residual stresses

🔴 CRITICAL RISK: If NaOH is stored above 40°C at concentrations >25%, or above 60°C at any concentration, SS304L is NOT a suitable material. This must be confirmed by the client's process team and a materials engineer before PO award. No vendor has raised this risk.

### 5.3 Sensitisation Risk in SS304 (Credo's Grade)

Standard SS304 has max carbon of 0.08% vs SS304L's max of 0.030%

During welding, the heat-affected zone (HAZ) of SS304 can reach 425–870°C

At this temperature range, chromium carbide precipitates at grain boundaries — this is sensitisation

Sensitised SS304 in NaOH service is vulnerable to intergranular corrosion and SCC

SS304L (low carbon) resists sensitisation because there is insufficient carbon to form chromium carbides

Credo must confirm SS304L is used, not standard SS304

### 5.4 Iron Contamination Risk

During fabrication, if carbon steel tools, grinding discs, or wire brushes are used on the stainless steel:

- Free iron is embedded in the SS surface

- In the presence of NaOH, this iron causes localised pitting

Requirement: All fabrication must use SS-dedicated tools only (no carbon steel)

Post-fabrication: Full passivation per ASTM A380 (not just HF acid cleaning) removes iron contamination and restores passive film

This must be specified in the ITP and welding procedure

### 5.5 NaOH-Specific Nozzle and Accessory Requirements

The following tank accessories are essential for NaOH service but not stated by any vendor:

| Accessory | Purpose | Status |
| --- | --- | --- |
| Internal sump/drain pocket | Complete drainage of NaOH (no heel) | ❌ Not stated by any vendor |
| Dip plate on fill nozzle | Prevents NaOH impingement directly on shell | ❌ Not stated |
| Anti-vortex plate on suction | Prevents vortex at pump suction nozzle | ❌ Not stated |
| Stilling well / gauging tube | Level instrument accuracy and protection | ❌ Not stated |
| Fixed cone roof vent/PV valve | Prevent vacuum on pump-out / overpressure | ❌ Not stated |
| Roof drain / sump | Drain rainwater from cone roof | ❌ Not stated |
| Shell manhole (20" min) | Internal access for inspection and cleaning | ❌ Not confirmed |
| Roof manhole | Roof access for vent/instrument installation | ❌ Not confirmed |
| Cleanout door/nozzle | Bottom flush and cleanout | ❌ Not stated |
| Earth/grounding lugs | Static grounding per SS code | ❌ Not stated |
| Settlement gauge bolts | Measure differential settlement | ❌ Not stated |
| Overfill protection nozzle | Connection for level high-high switch | ❌ Not stated |
| Temperature nozzle | Process temperature monitoring | ❌ Not stated |
| Sample point | QC sampling of NaOH | ❌ Not stated |
| Spare nozzles (minimum 2) | Future process modifications | ❌ Not stated |
| Wind girder (top) | Structural stability for H/D>1.5 | ❌ Not stated (required for Credo/Synergex) |

## SECTION 6 — API 650 COMPLIANCE REVIEW

### 6.1 API 650 Standard Requirements vs. Vendor Coverage

| API 650 Clause | Requirement | FES | Credo | Synergex |
| --- | --- | --- | --- | --- |
| Preamble | Code edition stated | ❌ | ❌ | ✅ 13th Ed. 2020 |
| §3.2 | Design conditions documented | ❌ | ❌ | ❌ |
| §3.3.2 | Corrosion allowance stated | ❌ | ❌ | ❌ |
| §3.6 | Shell thickness calculations | ❌ pending | ❌ | ❌ |
| §5.4 | Bottom plate minimum thickness | ❌ | ❌ | ❌ |
| §5.8 | Annular plate design | ❌ | ❌ | ❌ |
| §5.9 | Top wind girder (H/D check) | ❌ | ❌ required | ❌ required |
| §5.10 | Roof type and design | Cone (PPTX only) | ❌ | ❌ |
| §5.10 | Roof design pressure/vacuum | ❌ | ❌ | ❌ |
| §5.7 | Nozzle schedule | Ref. GA drawings | ❌ | ❌ |
| §5.7.3 | Shell manhole (min 20") | Not confirmed | ❌ | Included |
| §7.1 | WPS / PQR qualification | ❌ | ❌ | ❌ |
| §7.1 | Welder qualification (WPQ) | ❌ | ❌ | ❌ |
| §7.1.2 | Delta ferrite content check | ❌ | ❌ | ❌ |
| §8.1 | RT or UT — vertical shell joints | ❌ PT only | Partial UT | Vague |
| §8.2 | RT — horizontal shell joints | ❌ | ❌ | ❌ |
| §8.5 | Weld visual inspection | ✅ (implied) | ✅ (implied) | ✅ (implied) |
| §8.6 | Vacuum box test — bottom plates | ❌ | ❌ | ❌ |
| §7.3.6 | Hydrostatic test to max design level | ✅ | ❌ | ❌ explicit |
| §5.2 | Material mill certificates (MTRs) | ❌ | ❌ | ❌ |
| Annex B | API 650 Manufacturer's Data Report | ✅ MDR | ❌ | ❌ |
| Annex C | Internal pressure design (if applicable) | ❌ | ❌ | ❌ |
| Annex E | Seismic design | ❌ | ❌ | ❌ |
| Annex F | Variable design point (if used) | ❌ | ❌ | ❌ |
| §7.3.7 | Settlement monitoring | ❌ | ❌ | ❌ |

### 6.2 Critical API 650 Non-Conformances

NCR-01 — Shell Weld NDT Method (FES — CRITICAL)

API 650 §8.1 requires 100% RT or UT of all vertical shell butt joints. For tanks over 36m diameter with shell thickness <13mm, or tanks designed to the one-foot method, RT is mandatory for all vertical seams. PT is a surface-only examination (penetrates 0–3mm) and cannot detect subsurface defects such as porosity, incomplete fusion, slag inclusions, or cracks in the weld root. PT as the sole NDT method is a direct violation of API 650 §8.1 regardless of the ITP.

NCR-02 — No Vacuum Box Test (All vendors)

API 650 §8.6 mandates vacuum box testing of all horizontal and vertical bottom plate welds at minimum 6 psi vacuum. This detects bottom plate weld defects before hydrotest. Not one vendor mentions this mandatory test.

NCR-03 — No WPS/PQR (All vendors)

API 650 §7.1 requires all welding to be per qualified procedures (WPS) supported by Procedure Qualification Records (PQR) per ASME Section IX. This is non-negotiable. No vendor references these documents in their quotation.

NCR-04 — No Mill Certificates (All vendors)

API 650 §5.2 requires all steel to be furnished with certified mill test reports (MTRs) showing chemical composition and mechanical properties. For ASTM A240-304L, carbon content ≤0.030% must be verified per heat by MTR. Fabrication cannot proceed without this.

NCR-05 — Freeboard/Capacity Shortfall (FES)

FES tank at 11,450mm × 15,400mm provides only 1,585 m³ geometric volume. With API 650-required freeboard, working capacity falls to 1,506–1,554 m³. The tank must be redesigned with a minimum shell height of 15,840 mm to achieve 1,600 m³ working capacity.

NCR-06 — Wind Girder Omission (Credo and Synergex)

API 650 §5.9 requires a top wind girder for tanks where the H/D ratio exceeds certain limits. Both Credo (H/D=2.05) and Synergex (H/D=2.30) require a top wind girder and likely an intermediate shell stiffener ring to prevent shell buckling under wind load or vacuum conditions.

NCR-07 — Material Grade Ambiguity (Credo)

Credo specifies "SS304" without confirming the L-grade. For welded construction per API 650, the material must meet ASTM A240 Grade 304L (max C=0.030%). Standard 304 (max C=0.080%) is susceptible to sensitisation in the weld HAZ and is less suitable for NaOH service.

NCR-08 — Delta Ferrite Content (All vendors)

API 650 and ASME Section IX require austenitic SS weld metal to contain 3–8% ferrite (FN 3–8 per WRC-1992 diagram) to prevent hot cracking. No vendor mentions ferrite content control in their NDT/weld quality plan.

## SECTION 7 — BUND WALL CONTAINMENT ANALYSIS

### 7.1 Regulatory Requirement

NEA (Environmental Protection and Management Act) and SCDF (Fire Code) require secondary containment (bund) to hold ≥110% of the volume of the largest single storage vessel within the bund.

Largest single tank: 1,600 m³

Required minimum containment volume: 1,600 × 1.10 = 1,760 m³

### 7.2 FES Bund Assessment (From PPTX)

Tank ID: 11,450 mm → footprint per tank = π/4 × 11.45² = 102.95 m²

2 tanks total footprint: 205.9 m²

Foundation raises tank bottom: 1,700 mm above existing grade

Bund wall height stated: 2,100 mm above existing grade

Effective containment height above tank bottom: 2,100 − 1,700 = 400 mm only

For 1,760 m³ containment at 400 mm effective height:

Required net bund floor area: 1,760 / 0.40 = 4,400 m²

This equates to a ~66 m × 66 m bund — clearly impractical

Even if bund wall height referenced from tank bottom level (not ground):

At 2,100 mm wall height above existing grade with tanks at existing grade level:

Net bund area (less 2 tanks): (at minimum 30 m × 30 m bund) = 900 − 205.9 = 694 m²

Containment volume: 694 × 2.1 = 1,457 m³ — Insufficient (need 1,760 m³)

🔴 CRITICAL: FES bund wall at 2,100 mm height is insufficient to contain 1,760 m³ given the 1,700 mm foundation height and any reasonable bund footprint.

### 7.3 Credo Bund Assessment

Tank footprint: π/4 × 10² = 78.54 m²

2 tanks: 157.1 m²

Bund wall height: 2,200 mm

Bund plan area not stated. Estimating comparable to Synergex at 17 m × 30 m = 510 m²

Net bund area: 510 − 157.1 = 352.9 m²

Containment volume: 352.9 × 2.2 = 776 m³ — Grossly insufficient (need 1,760 m³)

🔴 CRITICAL: Credo's 2.2 m bund wall is less than half the required containment capacity.

### 7.4 Synergex Bund Assessment

Tank footprint: 78.54 m² × 2 = 157.1 m²

Bund plan area: 17 m × 30 m = 510 m²

Net bund area: 510 − 157.1 = 352.9 m²

Bund wall height: 4,000 mm

Containment volume: 352.9 × 4.0 = 1,412 m³ — Still insufficient (need 1,760 m³)

🟡 POTENTIAL: Synergex's 4,000 mm bund is closest to compliant but still 19% short of required containment volume.

### 7.5 Minimum Required Bund Parameters

To achieve 1,760 m³ containment for 1,600 m³ NaOH tanks (10 m diameter):

| Scenario | Bund Footprint | Required Wall Height |
| --- | --- | --- |
| Single shared bund (2 tanks, 10m dia) | 20 m × 30 m = 600 m² | 1,760/(600−157) = 3.97 m ≈ 4.0 m |
| Single shared bund (2 tanks, 10m dia) | 25 m × 30 m = 750 m² | 1,760/(750−157) = 2.97 m ≈ 3.0 m |
| Separate bunds (1 tank each, 10m dia) | 20 m × 20 m = 400 m² | 1,760/(400−79) = 5.48 m |
| FES: shared bund (2 tanks, 11.45m dia) | 30 m × 30 m = 900 m² | 1,760/(900−206) = 2.54 m |

Recommendation: For a shared bund accommodating both 10 m dia tanks, a minimum bund wall of 4.0 m at a footprint of at least 20 m × 30 m is required. For FES's larger-diameter tanks (11.45 m), a 30 m × 30 m bund with 2.5 m effective walls (above tank bottom elevation) is the minimum.

## SECTION 8 — SINGAPORE REGULATORY COMPLIANCE REVIEW

### 8.1 Ministry of Manpower (MOM) — Workplace Safety & Health

Applicable Legislation:

Workplace Safety and Health Act (WSHA) Cap 354A

WSH (Construction) Regulations 2007

WSH (Risk Management) Regulations 2006

WSH (Work at Heights) Regulations 2013

WSH (Confined Spaces) Regulations 2009

WSH (Operation of Cranes) Regulations 2011

| MOM Requirement | FES | Credo | Synergex | Risk if Missing |
| --- | --- | --- | --- | --- |
| MSRA (Method Statement & Risk Assessment) | ✅ Stated | ❌ Not stated | ❌ Not stated | MOM stop-work order |
| Safety documentation for worksite | ✅ Referenced | ❌ | ❌ | Non-compliance with WSHA |
| ELCB for electrical equipment | ✅ Stated | ❌ | ❌ | Electrical fatality risk |
| Scaffold PE endorsement (>30m height) | ❌ Not stated | ❌ | ❌ | MOM stop-work order; collapse risk |
| Confined space entry procedure (tank interior) | ❌ Not stated | ❌ | ❌ | Worker fatality in NaOH atmosphere |
| Hot work PTW (Permit to Work) system | ❌ Not stated | ❌ | ❌ | Fire/explosion risk without PTW |
| MOM-registered crane + COC operator | ✅ Crane contractor: Denzai | ❌ | ❌ | Illegal crane operation; MOM prosecution |
| Lifting Supervisor (LS) certificate for all lifts | ❌ Not stated | ❌ | ❌ | Illegal lifting; risk of dropped load |
| Appointed Person (AP) for crane lifts >1t | ❌ Not stated | ❌ | ❌ | MOM §12 WSHA liability |
| WSH Officer / Safety Coordinator | ❌ Not stated | ❌ | ❌ | Non-compliance for project >S$30M (WSHO needed) |
| Safety Plan submission to MOM | ❌ Not stated | ❌ | ❌ | Required before construction commences |
| ASPRI Jurong Island HSSE requirements | ❌ Not stated | ❌ | ❌ | JTC / ASPRI may deny site access |

Key MOM Gaps (All Vendors):

Confined space entry for tank interior: Tank interior during erection and cleaning is a confined space. Caustic soda atmosphere, lack of oxygen, and welding fumes make this a high-hazard confined space. A dedicated confined space entry procedure and rescue plan is mandatory per WSH (Confined Spaces) Regulations 2009.

Working at heights: With tanks up to 23 m tall, WSH (Work at Heights) Regulations 2013 requires specific controls at every working level. Scaffolding design must be endorsed by a PE for scaffolds above certain heights.

Lifting operations: Every lift must have a Lifting Plan signed by an Appointed Person (AP). For tanks, this includes roof plates, shell plates, and crane rigging. None of the vendors have confirmed AP appointment.

### 8.2 Building and Construction Authority (BCA)

Applicable Legislation:

Building Control Act (Cap 29)

Building Control Regulations 2003

Building Control (Accreditation of Registered Inspectors) Regulations

BC Piling Regulations

| BCA Requirement | FES | Credo | Synergex | Risk if Missing |
| --- | --- | --- | --- | --- |
| Qualified Person (QP) — Structural submission | ✅ K P Koh & Partners (from PPTX) | ✅ Referenced | ✅ PE submission included | BCA will not approve |
| BCA piling submission and approval | ❌ Not detailed | ✅ Detailed (146 micropiles) | Partial (250 piles) | Cannot begin piling without approval |
| Registered piling contractor (Class MB2 or above) | ❌ Not stated | Not stated | Not stated | Illegal piling; BCA stop work |
| Resident Technical Officer (RTO) | ❌ Not stated | ✅ Included (SGD 20,000) | Not stated | Required for projects >S$2M construction value |
| Structural calculations (PE endorsed) | ✅ K P Koh | ✅ Referenced | ✅ Referenced | Cannot obtain BCA approval without |
| Topographic survey and as-built submission | ✅ In scope | ✅ Included | ❌ Not stated | Cannot obtain CSC/TOP |
| TOP / CSC application | Not stated | ✅ Referenced | ❌ Not stated | Structure cannot be legally occupied |
| BCA registered builder | Not confirmed | Not confirmed | Not confirmed | Mandatory for building works >S$250K |
| Piling load test (static, PDA, PIT) | ❌ Not stated | ✅ Included | ❌ Not stated | BCA may require proof of pile capacity |

Key BCA Observation:

Credo is the most BCA-compliant in terms of regulatory submissions — they include JTC, URA, BCA, SCDF, LTA(VP), NParks, NEA and PUB, RTO, registered surveyor, topographic survey and as-built drawings. FES does not explicitly list all these authorities. Synergex only mentions BCA and PE. All three must ensure a BCA registered builder is engaged.

### 8.3 Land Transport Authority (LTA)

Applicable Legislation:

Road Traffic Act (Cap 276)

LTA Abnormal Load Permit System

LTA Vehicle Permits

| LTA Requirement | FES | Credo | Synergex | Risk |
| --- | --- | --- | --- | --- |
| Abnormal load permit for crane transport | ❌ Not stated | ✅ LTA(VP) included | ❌ Not stated | Illegal heavy vehicle movement; vehicle impoundment |
| Traffic Management Plan (TMP) for lane closures | ❌ Not stated | ❌ Not stated | ❌ Not stated | Road safety violation |
| Heavy vehicle (prime mover) access to Jurong Island | ❌ Not stated | Implied in LTA(VP) | ❌ Not stated | Jurong Island access control for heavy vehicles |
| Overheight/overwidth vehicle permits | ❌ Not stated | ❌ Not stated | ❌ Not stated | Required for long shell plate transport |

Note on Jurong Island Access:

Jurong Island has controlled access via the Jurong Island Highway (managed by JTC). All heavy vehicles, cranes, and abnormal loads must obtain prior clearance from JTC and relevant authorities. This process can take 2–4 weeks and must be planned into the project schedule. No vendor has addressed this specifically.

### 8.4 JTC Corporation (Jurong Island)

| JTC Requirement | FES | Credo | Synergex | Risk |
| --- | --- | --- | --- | --- |
| JTC development approval for new tanks | ❌ Not explicit | ✅ JTC submission included | ❌ Not stated | Cannot construct without JTC approval |
| JTC Permit to Proceed (PTP) | ❌ Not stated | Implied | ❌ Not stated | JTC stop work; no site access |
| JTC Fire Safety requirements | ❌ Not stated | Partial | ❌ Not stated | JTC non-compliance |
| ASPRI HSSE Induction for workers | ❌ Not stated | ❌ Not stated | ❌ Not stated | Workers denied site access |
| JTC approved chemical storage guidelines | ❌ Not stated | ❌ Not stated | ❌ Not stated | JTC non-compliance for NaOH storage |
| JTC approval for bund design | ❌ Not stated | Implied | ❌ Not stated | Cannot obtain JTC occupancy |

### 8.5 National Environment Agency (NEA)

| NEA Requirement | FES | Credo | Synergex | Risk |
| --- | --- | --- | --- | --- |
| NEA hazardous substance storage license (NaOH) | Not in scope | ✅ NEA submission | Not in scope | Cannot store NaOH legally |
| Bund containment ≥110% largest tank | ❌ Insufficient (calc'd) | ❌ Insufficient (calc'd) | ❌ Insufficient (calc'd) | NEA regulatory non-compliance |
| Drainage system for bund (to chemical sump) | ❌ Not stated | Partial (drain/sump in BQ) | Not stated | Environmental discharge violation |
| Environmental monitoring during construction | ❌ Not stated | ❌ Not stated | ❌ Not stated | NEA enforcement action |
| Chemical spill emergency plan | Not in scope | Not in scope | Not in scope | Client responsibility; NEA requirement |

### 8.6 SCDF (Singapore Civil Defence Force)

| SCDF Requirement | FES | Credo | Synergex | Risk |
| --- | --- | --- | --- | --- |
| SCDF fire safety plan submission | ❌ Not stated | ✅ SCDF included | ❌ Not stated | Cannot obtain Fire Safety Certificate (FSC) |
| Fire Safety Certificate (FSC) | ❌ Not stated | Implied | ❌ Not stated | Cannot commission tanks legally |
| NaOH bund design per SCDF Fire Code | ❌ Not designed | Partial | Partial | SCDF rejection of bund design |
| Emergency access around tanks | ❌ Not stated | ❌ Not stated | ❌ Not stated | SCDF non-compliance |
| Chemical storage labelling / placarding | Not in scope | Not in scope | Not in scope | Client responsibility |

### 8.7 Regulatory Compliance Summary

| Authority | FES | Credo | Synergex |
| --- | --- | --- | --- |
| MOM (WSH) | Partial ✅/❌ | Partial | Partial |
| BCA | Partial (PE confirmed) | Most Complete ✅ | Partial |
| LTA | Not stated | ✅ LTA(VP) included | Not stated |
| JTC (Jurong Island) | Not explicit | ✅ Included | Not stated |
| NEA | Not explicit | ✅ Included | Not stated |
| SCDF | Not explicit | ✅ Included | Not stated |
| PUB | ✅ Water for hydrotest | ✅ Included | Not stated |
| URA | Not stated | ✅ Included | Not stated |
| Regulatory Completeness | LOW | HIGH | LOW |

Observation: Credo's regulatory submission coverage is significantly more thorough than FES or Synergex. However, the regulatory submission service alone cannot justify a SGD 1.3M price premium. The client should instruct FES and Synergex to explicitly confirm they will cover all regulatory submissions required for a Jurong Island chemical storage project.

## SECTION 9 — INSPECTION, QUALITY & DOCUMENTATION REVIEW

| QA/QC Element | FES | Credo | Synergex | Required? |
| --- | --- | --- | --- | --- |
| ITP (Inspection & Test Plan) | ✅ Mentioned | ❌ | ❌ | Mandatory for API 650 |
| MDR (Manufacturer's Data Record) | ✅ Included | ❌ | ❌ | Mandatory for API 650 |
| API 650 Manufacturer's Data Report Form | ❌ not explicit | ❌ | ❌ | Mandatory per API 650 Annex B |
| WPS (Weld Procedure Specification) | ❌ | ❌ | ❌ | Mandatory — API 650 §7.1 |
| PQR (Procedure Qualification Record) | ❌ | ❌ | ❌ | Mandatory — API 650 §7.1 |
| WPQ (Welder Performance Qualification) | ❌ | ❌ | ❌ | Mandatory — API 650 §7.1 |
| Delta ferrite content control | ❌ | ❌ | ❌ | Recommended for SS304L welds |
| MTRs for all SS plates/fittings | ❌ | ❌ | ❌ | Mandatory — API 650 §5.2 |
| Heat trace/lot traceability | ❌ | ❌ | ❌ | Required for pressure-retaining parts |
| NDT — Vertical shell joints (RT or UT) | ❌ PT only | Partial UT | "UT etc." | Mandatory — API 650 §8.1 |
| NDT — Horizontal shell joints | ❌ | ❌ | ❌ | Required — API 650 §8.2 |
| NDT — Bottom plate welds | ❌ | ❌ | ❌ | Vacuum box — API 650 §8.6 |
| NDT — Nozzle welds (PT or MT) | ❌ | ❌ | ❌ | Required |
| Visual inspection (VT) | ✅ implied | ✅ implied | ✅ implied | Required |
| Dimensional inspection (plumb, roundness) | ✅ calibration | ❌ | ❌ | Required per API 650 §7.5 |
| Hydrostatic test — Tank | ✅ full height | ❌ not stated | ❌ not explicit | Mandatory — API 650 §7.3.6 |
| Hydrostatic test — Piping | ✅ | Not applicable | N/A | Required per ASME B31.3 |
| Vacuum box test — Bottom plates | ❌ | ❌ | ❌ | Mandatory — API 650 §8.6 |
| Passivation per ASTM A380 | ❌ (HF only) | Partial | ✅ | Required for SS NaOH service |
| Post-weld cleaning (SS-dedicated tools) | ❌ | ❌ | ❌ | Required to prevent Fe contamination |
| Tank survey (plumb, roundness, settlement) | ✅ SGD 5,000 | ❌ | ❌ | API 650 §7.5 |
| Foundation settlement survey post-hydrotest | ❌ | ❌ | ❌ | Best practice; Jurong Island reclaimed land |
| PSSR (Pre-Startup Safety Review) | ✅ Slide 17 | ❌ | ❌ | Best practice; MOM/client requirement |
| As-built drawings | ❌ not explicit | Survey only | ❌ | Required for handover |
| Calibration chart / strapping table | ✅ included | ❌ | ❌ | Required for inventory management |
| NDT company accreditation (SAC-SINGLAS) | SNDT — unverified | ❌ not stated | ❌ not stated | MOM/API requirement |

NDT Company Note: FES has named SNDT as the NDT contractor. SAC-SINGLAS (Singapore Accreditation Council) accreditation for RT, UT, and PT methods must be confirmed. For API 650 compliance, the NDT contractor must use qualified NDE Level II or III technicians (ASNT or equivalent). This must be verified before PO.

## SECTION 10 — COMMERCIAL RISK REVIEW

### 10.1 Scope Gap & Hidden Cost Analysis

| Risk Item | FES | Credo | Synergex | Estimated Cost if Variation |
| --- | --- | --- | --- | --- |
| Lightning protection | Not included | ✅ SGD 35,000 | ✅ SGD 57,200 | SGD 30,000–60,000 |
| Painting spec upgrade | Low allowance (SGD 12,500) | Not included | Not included | SGD 20,000–50,000/tank |
| Full passivation per ASTM A380 | HF only | Partial | ✅ | SGD 15,000–30,000/tank |
| Vacuum box test | ❌ | ❌ | ❌ | SGD 5,000–10,000 |
| Tank height increase (FES only) | Needs 440mm more | N/A | N/A | SGD 20,000–40,000 |
| Wind girder (Credo/Synergex) | Not needed | Not stated | Not stated | SGD 15,000–25,000/tank |
| Bund wall height increase | Likely variation | Likely variation | Likely variation | SGD 80,000–200,000 |
| Settlement monitoring | ❌ | ❌ | ❌ | SGD 5,000–15,000 |
| Overfill protection (API 2350) | ❌ | ❌ | ❌ | SGD 20,000–40,000 |
| Third-party inspection (TPI) | ❌ | ❌ | ❌ | SGD 20,000–35,000 |
| Internal sump, dip plate, anti-vortex | ❌ | ❌ | ❌ | SGD 10,000–20,000 |
| Warranty / defects liability | Not stated | Not stated | Not stated | Contractual risk |
| RT or UT upgrade (FES) | PT only | Partial | Partial | SGD 15,000–30,000 |

Estimated potential variation cost for FES (if all gaps become VOs): SGD 220,000–530,000

Even with worst-case variations, FES remains significantly cheaper than competitors.

### 10.2 Exclusions Risk Summary

Falkor (FES) — 4 Named Exclusions (Manageable Risk)

Instruments and specialty items — acceptable; client scope

E&I works — acceptable; by Radiant Electrical (named)

Insulation — acceptable if NaOH temperature confirmed <40°C

Underground obstructions — standard industry exclusion

Credo E&C — Broad Exclusion Clause (HIGH RISK)

*"Any scope not listed in BQ shall be excluded."*

Combined with the absence of hydrotest, ITP, MDR, weld procedures, and many API 650 requirements in the BQ, this exclusion clause creates extremely high variation order risk. Every missing item becomes a separate negotiation.

Synergex — Implicit Broad Exclusion (MODERATE RISK)

*"All other works, items and parts not specifically stated in the above quote."*

Painting/coating is a notable confirmed omission. This clause also excludes hydrotest if not specifically stated.

### 10.3 Commercial Terms Comparison

| Term | FES | Credo | Synergex |
| --- | --- | --- | --- |
| Payment — Downpayment | 20% | Not agreed | 20% (on drawing approval) |
| Payment — Progress | Monthly claims | "To be discussed" | Milestones (5 stages) |
| Payment — Final | 30 days from invoice | "To be discussed" | 10% on T&C |
| Performance Bond | Offered | Waived | Not stated |
| Liquidated Damages | Not stated | Explicitly excluded | Not stated |
| Warranty | Not stated | Not stated | Not stated |
| Validity | 30 days | 30 days | 14 days only |
| GST | Stated (not included) | Excluded | Excluded |
| Delivery commitment | 36-week schedule | None | "TBA" |

## SECTION 11 — CIVIL / FOUNDATION ENGINEERING REVIEW

### 11.1 Pile Design Comparison

| Parameter | FES (Falkor) | Credo | Synergex |
| --- | --- | --- | --- |
| Pile type | Unknown | Micropile (bored) | RC jack-in (precast) |
| Pile diameter / section | Unknown | 200 mm dia | 200 × 200 mm |
| Pile length | Unknown | 33 m | 12 m |
| Piles per tank | 20 | 74 | 125 |
| Total piles (2 tanks) | 40 | 148 | 250 |
| Load tests included | Not stated | ✅ Static, PDA, PIT | ❌ Not stated |
| Foundation slab | Not stated | 350 mm RC | 400 mm RC |
| Bund wall H | 2,100 mm | 2,200 mm | 4,000 mm |
| Bund wall thickness | Not stated | 200 mm | 250 mm |
| Soil investigation | Topo survey (not SI) | Not stated | Not stated |
| Civil sub-total (est./tank) | SGD 510,000 | SGD 720,000 | SGD 579,300 |

### 11.2 Foundation Load Calculations

For NaOH at SG = 1.40 (typical 40% w/w solution):

| Load Component | FES Tank (11.45m) | Credo/Synergex Tank (10m) |
| --- | --- | --- |
| NaOH fluid weight | 1,600 × 1.40 = 2,240 t = 21,970 kN | 1,600 × 1.40 = 2,240 t |
| Tank dead weight | ~90 t = 882 kN | ~85 t = 833 kN |
| Total operating load | ~22,852 kN | ~22,803 kN |
| Hydrotest water weight | 1,600 × 1.0 = 1,600 t = 15,696 kN | 1,600 t = 15,696 kN |
| Total hydrotest load | ~16,578 kN | ~16,529 kN |
| Tank base area | π/4 × 11.45² = 102.95 m² | π/4 × 10² = 78.54 m² |
| Operating bearing pressure | 22,852 / 102.95 = 222 kPa | 22,803 / 78.54 = 290 kPa |

For FES's 20-pile design:

Total design load = 22,852 kN (operating) or 16,578 kN (hydrotest)

Load per pile = 22,852 / 20 = 1,143 kN/pile (operating, no safety factor)

A 200 mm micropile in reclaimed marine clay at 33 m depth typically carries 300–600 kN

At 500 kN/pile capacity: 20 piles = 10,000 kN total — only 44% of required capacity

This pile design is critically inadequate for the tank loads

Even at an optimistic 800 kN/pile: 20 × 800 = 16,000 kN — only 70% of operating load

🔴 CRITICAL: FES's 20-pile design cannot support the tank loads on Jurong Island reclaimed land. This is not a small discrepancy — it is a fundamental structural safety issue.

For Credo's 74-pile design (micropile at 33m):

At 500 kN/pile capacity: 74 × 500 = 37,000 kN — adequate (1.6× safety factor on operating load)

Load tests included — provides verification of actual capacity

This design is plausible and more consistent with Jurong Island ground conditions

For Synergex's 125-pile design (jack-in at 12m):

Jack-in piles at 12m in marine clay: typically 200–350 kN per pile

At 250 kN/pile: 125 × 250 = 31,250 kN — marginal (1.4× on operating load)

No load tests stated — pile capacity unverified

12 m depth may be insufficient to reach competent bearing layer at Sakra Avenue

## SECTION 12 — PROJECT SCHEDULE REVIEW

Only FES has provided a project schedule.

| Activity | Duration | Month |
| --- | --- | --- |
| Engineering & Authority Submission | 16 weeks | Jul – Oct 2026 |
| Site Setup & Mobilisation | 1 week | Aug 2026 |
| Civil Piling Works | 12 weeks | Sep – Nov 2026 |
| Tank Foundation & Bund Wall | 8 weeks | Oct – Dec 2026 |
| Piping Material Procurement | 3 weeks | Jul 2026 |
| Piping Scaffolding | 4 weeks | Aug 2026 |
| Piping Pre-fabrication | 2 weeks | Sep 2026 |
| Pipe Spool Erection | 6 weeks | Sep – Oct 2026 |
| Tank Material Procurement | 5 weeks | Aug – Sep 2026 |
| Tank Pre-fabrication | 6 weeks | Oct – Nov 2026 |
| Tank Erection (both tanks) | 16 weeks | Nov 2026 – Feb 2027 |
| Hydrostatic Test (both tanks) | 4 weeks | Feb – Mar 2027 |
| Tank Handover | 2 weeks | Mar 2027 |
| Total Program | ~36 weeks | Jul 2026 – Mar 2027 |

Schedule Gaps Noted:

No buffer for BCA/JTC approval delays (authority submissions typically take 8–12 weeks on Jurong Island)

16-week authority submission overlaps with civil works start — risk if approval is delayed

No ASPRI safety induction / JTC access clearance timeline shown

No allowance for rainy season impact (Nov–Jan northeast monsoon)

No commissioning or startup period shown post-handover

## SECTION 13 — RED FLAGS REGISTER (COMPREHENSIVE)

### 🔴 CRITICAL ISSUES

| Ref | Vendor | Issue | Applicable Code / Reg | Consequence |
| --- | --- | --- | --- | --- |
| C-01 | FES | PT only for shell weld NDT. API 650 §8.1 mandates RT or UT for all vertical shell butt welds. PT is surface-only (0–3mm depth). Cannot detect subsurface porosity, incomplete fusion, or root cracks. | API 650 §8.1–8.2 | Weld defect passes hydrotest, fails in NaOH service. Tank rejection by authority. |
| C-02 | FES | 20 piles per tank structurally insufficient. Load calculation shows 44–70% of required pile capacity depending on assumed pile working load. Foundation failure risk on Jurong Island reclaimed land. | BCA Piling Regs; WSHA | Differential settlement, tank distortion, shell cracking, catastrophic NaOH spill. |
| C-03 | FES | Tank undersized. 11,450mm × 15,400mm gives only 1,585 m³ geometric volume. With API 650 freeboard (min 300mm), working capacity ≈ 1,554 m³ — 46 m³ short of specified 1,600 m³. | API 650 §1.1.1 | Client receives 97% of specified capacity. Process impact. |
| C-04 | Credo | No hydrostatic test in BQ. Broad exclusion clause means hydrotest is excluded. Hydrotest is a mandatory API 650 requirement that cannot be omitted. | API 650 §7.3.6 | Non-compliant tank. Major variation order claim post-award. |
| C-05 | Credo | No liquidated damages, no performance bond. For SGD 4M project on Jurong Island with chemical plant uptime implications. | Commercial | No schedule accountability. Vendor can delay indefinitely without financial consequence. |
| C-06 | Synergex | No delivery schedule. "TBA upon order confirmation" is unacceptable. Cannot plan commissioning, production, regulatory compliance, or manpower. | Commercial | Complete schedule uncertainty. No basis for planning. |
| C-07 | Synergex | No painting/coating in scope. External coating essential for a 20+ m SS tank in tropical coastal Jurong Island environment. | — | Major unbudgeted variation order. Corrosion if coating not applied. |
| C-08 | All | No WPS/PQR provided. All welding must be to qualified procedures per API 650 §7.1 / ASME Section IX. No vendor references weld procedures. | API 650 §7.1; ASME IX | Unqualified welding. Weld quality unverifiable. Tank may fail NDT. |
| C-09 | All | No mill certificates (MTRs). ASTM A240-304L must have certified MTRs per heat, traceable to each plate. Without MTRs, material cannot be verified as compliant. | API 650 §5.2; ASTM A240 | Material non-conformance. Carbon content may exceed 304L limit (0.030%). Sensitisation risk. |
| C-10 | All | Bund wall containment insufficient (all vendors). NEA requires ≥110% of largest tank (1,760 m³). Calculated containment for all three vendors falls short. FES worst at 400mm effective height. | NEA EPMA; SCDF Fire Code | Regulatory non-compliance. NEA may reject installation. Environmental liability in spill. |
| C-11 | All | No Caustic SCC risk assessment. SS304L susceptibility to caustic stress corrosion cracking at elevated temperatures (>40°C at 25–50% NaOH). No vendor has addressed this critical material risk. | NACE SP0169; Corrosion literature | Premature tank failure if NaOH temperature exceeds threshold. Catastrophic spill risk. |
| C-12 | All | No vacuum box test for bottom plates. API 650 §8.6 mandates vacuum box testing of all horizontal and vertical bottom plate welds. Not mentioned by any vendor. | API 650 §8.6 | Bottom plate weld defects not detected. Potential through-leak of NaOH into foundation. |
| C-13 | All | Three vendors pricing completely different tank geometries (11.45m × 15.4m vs 10m × 20.5m vs 10m × 23m). Tenders are not comparable without a common Design Basis. | Procurement best practice | Award made on non-comparable basis. Scope disputes post-award. |

### 🟡 POTENTIAL ISSUES

| Ref | Vendor | Issue | Risk |
| --- | --- | --- | --- |
| P-01 | FES | HF acid cleaning ≠ full passivation per ASTM A380. HF removes heavy scale only. ASTM A380 passivation (nitric acid or citric acid treatment) removes free iron contamination and restores Cr₂O₃ passive film critical for NaOH resistance. | Premature pitting; corrosion under NaOH |
| P-02 | FES | Painting budget SGD 12,500/tank is very low. For a 11.45m × 15.4m tank (circumference 36m × height 15.4m = 554 m² external area), typical industrial coating at SGD 30–50/m² = SGD 16,600–27,700. | Coating failure; corrosion; rework cost |
| P-03 | FES | Foundation sits 1,700mm above grade. Effective bund containment height above tank bottom is only 400mm — wholly inadequate for NEA requirements. | NEA non-compliance; spill containment failure |
| P-04 | FES | SNDT as NDT contractor — accreditation not verified. Must confirm SAC-SINGLAS accreditation for applicable NDT methods and ASNT Level II technicians. | Unacceptable NDT results; API 650 non-compliance |
| P-05 | Credo | SS304 without L-grade confirmation. Standard 304 (0.08% max C) is susceptible to sensitisation during welding. For NaOH service, 304L is essential. | Intergranular corrosion in weld HAZ |
| P-06 | Credo | Passivation material to be supplied by CIL. This splits responsibility. Credo applies, CIL supplies. If passivation is incomplete, both parties dispute accountability. | Accountabiltiy gap; ineffective passivation |
| P-07 | Credo | 2.2m bund wall contains only ~776 m³ — 44% of required 1,760 m³. | NEA non-compliance |
| P-08 | Credo | 12 weeks for piping erection shown in FES schedule — Credo has no schedule, so piping completion date unknown. Connection to existing tanks may conflict with plant operations. | Production impact; tie-in planning risk |
| P-09 | Synergex | 23m overall height for 10m dia tank: H/D = 2.30. Wind girder is definitely required. Not stated in scope. | Shell buckling under wind/vacuum |
| P-10 | Synergex | NDT stated as "UT etc." — no standard (ASME, EN, AWS), no frequency, no acceptance criteria. This cannot be enforced in an ITP. | Vague NDT; unenforceable quality requirement |
| P-11 | Synergex | No settlement monitoring after hydrotest. 250 piles at 12m depth on reclaimed land — need post-hydrotest survey to confirm uniform settlement within API 650 limits. | Undetected differential settlement |
| P-12 | All | No hot work permit (PTW) system referenced. Arc welding on SS304L tanks containing weld fumes and carbon monoxide in confined spaces is an immediate MOM WSH violation risk. | MOM stop-work; worker health risk |
| P-13 | All | No confined space entry procedure for tank interior. Tank interior is a confined space under WSH (Confined Spaces) Regulations 2009. Confined space entry without rescue plan and gas monitoring is illegal. | Worker fatality; MOM prosecution |
| P-14 | All | No overfill protection per API 2350. API 2350 (Overfill Protection for Storage Tanks) requires level monitoring, high-high switches, and SIL assessment for tanks receiving NaOH by pump. | Tank overflow; NaOH spill; environmental incident |
| P-15 | All | No warranty period stated by any vendor. For a SGD 2.8–4.1M project, absence of any warranty clause creates post-handover dispute risk. | Legal liability gap |
| P-16 | All | No anti-vortex plate on suction nozzle, no dip plate on fill nozzle. Standard equipment for NaOH tanks to prevent shell impingement and pump vortex. | Shell corrosion at impingement point; pump cavitation |
| P-17 | All | No roof vent / pressure-vacuum relief device specified. Fixed cone roof requires PV valve to prevent vacuum collapse on pump-out and overpressure on filling. | Roof structural damage; potential shell collapse |
| P-18 | All | No drain sump (internal). NaOH tanks require a sump at the lowest point of the bottom plate to allow complete draining. Without a sump, NaOH heel remains after draining. | Residual NaOH heel; cleaning difficulty; safety risk |

### 🟠 CLARIFICATIONS REQUIRED

| Ref | Vendor | Clarification |
| --- | --- | --- |
| CL-01 | FES | Confirm RT or UT (not PT) for vertical shell welds per API 650 §8.1. Provide revised NDT plan with method, standard, frequency, extent, and acceptance criteria. |
| CL-02 | FES | Explain basis for 20 piles per tank. Provide pile type, diameter, length, design working load per pile, factor of safety, and geotechnical reference. |
| CL-03 | FES | Tank at 11,450mm × 15,400mm gives 1,585 m³ only. Confirm how 1,600 m³ working capacity is achieved with API 650 freeboard. Will height be increased to minimum 15,840mm? |
| CL-04 | FES | Confirm full passivation per ASTM A380 is included, not only HF cleaning. |
| CL-05 | FES | Provide painting/coating specification: surface prep standard, primer, topcoat, DFT, applicable standard. Confirm SGD 12,500/tank covers full external coating of a 554 m² tank. |
| CL-06 | FES | Confirm CAR + PL insurance coverage and limits. Are they embedded in "Indirect Cost & Site Facilities"? |
| CL-07 | FES | State warranty/defects liability period and remedy terms. |
| CL-08 | FES | Confirm SNDT holds SAC-SINGLAS accreditation for the NDT methods to be used (PT, and upgraded to RT/UT). Confirm ASNT Level II technicians. |
| CL-09 | FES | Confirm all Singapore authority submissions: JTC, BCA, SCDF, NEA, LTA(VP), URA. Is this included or does it only cover PE endorsement? |
| CL-10 | FES | Confirm bund wall height and how NEA 110% containment (1,760 m³) will be achieved given 1,700mm foundation height. |
| CL-11 | Credo | Confirm hydrostatic testing to full water height is included in scope. |
| CL-12 | Credo | Confirm material grade is SS304L (max C=0.030%), not standard SS304. |
| CL-13 | Credo | Provide payment terms in full. "To be discussed" is not acceptable at quotation stage. |
| CL-14 | Credo | Confirm NDT standard, method, frequency, extent, and acceptance criteria for shell welds. |
| CL-15 | Credo | Confirm WPS/PQR, welder qualification, and MTRs are included in scope. |
| CL-16 | Credo | Confirm ITP and MDR/data book are included in scope. |
| CL-17 | Credo | Confirm bund wall height and demonstrate NEA 110% containment compliance. |
| CL-18 | Synergex | Confirm whether 23m is overall height or shell height. Confirm capacity ≥1,600 m³ at working level with API 650 freeboard applied. |
| CL-19 | Synergex | Confirm painting/external coating is in scope. If not, provide cost addition. |
| CL-20 | Synergex | Confirm hydrotest per API 650 §7.3.6 is included. Provide test pressure and hold duration. |
| CL-21 | Synergex | Confirm delivery schedule in weeks from PO. "TBA" is not acceptable. |
| CL-22 | Synergex | Confirm MDR, as-built drawings, and ITP are included. |
| CL-23 | All | State API 650 edition and applicable annexes. |
| CL-24 | All | State design wind speed basis (Singapore SS EN 1991-1-4 or equivalent). |
| CL-25 | All | State seismic design basis (API 650 Annex E if applicable to Singapore zone). |
| CL-26 | All | State design temperature range (min/max operating). |
| CL-27 | All | State design internal pressure and design external vacuum (for roof design). |
| CL-28 | All | State corrosion allowance applied and basis. |
| CL-29 | All | Confirm roof type and confirm top wind girder is included where H/D>1.5. |
| CL-30 | All | Confirm vacuum box testing of bottom plate welds is included per API 650 §8.6. |
| CL-31 | All | Confirm internal sump, dip plate on fill nozzle, anti-vortex on suction, and PV vent are included. |
| CL-32 | All | Confirm settlement monitoring survey after hydrotest is included. |
| CL-33 | All | Confirm NaOH operating temperature range. If >40°C, confirm caustic SCC risk assessment has been conducted and material selection validated. |
| CL-34 | All | State warranty period and defects liability period with remedy terms. |

## SECTION 14 — MISSING SCOPE SUMMARY

Short summary of items missing from ALL THREE quotations that are required for a fully compliant API 650 SS304L NaOH storage tank.

### A. Tank Design (API 650)

| # | Missing Item | Criticality |
| --- | --- | --- |
| 1 | Common Design Basis / Technical Specification issued by client | 🔴 Critical |
| 2 | API 650 edition confirmed | 🔴 Critical |
| 3 | Shell course thickness schedule | 🔴 Critical |
| 4 | Freeboard confirmed + capacity ≥1,600 m³ verified | 🔴 Critical |
| 5 | Roof type (cone/dome) and design pressure/vacuum | 🔴 Critical |
| 6 | Wind girder (top + intermediate) for H/D>1.5 | 🔴 Critical (Credo/Synergex) |
| 7 | Corrosion allowance | 🟠 Important |
| 8 | Wind speed design basis | 🟠 Important |
| 9 | Seismic design (Annex E check) | 🟠 Important |
| 10 | Bottom plate / annular plate design | 🟠 Important |

### B. NaOH Service Requirements

| # | Missing Item | Criticality |
| --- | --- | --- |
| 11 | Caustic SCC risk assessment | 🔴 Critical |
| 12 | NaOH concentration and temperature confirmed | 🔴 Critical |
| 13 | Material selection validation for SCC risk | 🔴 Critical |
| 14 | Internal sump/drain pocket | 🟡 Important |
| 15 | Dip plate on fill nozzle | 🟡 Important |
| 16 | Anti-vortex plate on suction nozzle | 🟡 Important |
| 17 | PV vent / roof vent for fixed cone roof | 🔴 Critical |
| 18 | Overfill protection per API 2350 | 🔴 Critical |
| 19 | Full passivation per ASTM A380 | 🟡 Important |
| 20 | SS-dedicated tools only (no Fe contamination) | 🟡 Important |

### C. Quality / Inspection (API 650)

| # | Missing Item | Criticality |
| --- | --- | --- |
| 21 | RT or UT for vertical shell welds | 🔴 Critical |
| 22 | Vacuum box test for bottom plate welds | 🔴 Critical |
| 23 | WPS / PQR (weld procedures) | 🔴 Critical |
| 24 | WPQ (welder qualification records) | 🔴 Critical |
| 25 | Mill certificates (MTRs) for all SS materials | 🔴 Critical |
| 26 | API 650 Manufacturer's Data Report (Form) | 🟡 Important |
| 27 | Delta ferrite content control in weld metal | 🟠 Important |
| 28 | Third-party inspection (TPI) agency | 🟡 Important |
| 29 | Settlement monitoring survey post-hydrotest | 🟡 Important |
| 30 | As-built drawings package | 🟡 Important |

### D. Singapore Regulatory

| # | Missing Item | Criticality |
| --- | --- | --- |
| 31 | Complete authority submissions: JTC, BCA, URA, SCDF, NEA, LTA, NParks, PUB | 🔴 Critical |
| 32 | Bund wall compliant with NEA 110% containment (1,760 m³) | 🔴 Critical |
| 33 | Fire Safety Certificate (SCDF) | 🔴 Critical |
| 34 | MOM safety plan, WSHO/Safety Coordinator | 🔴 Critical |
| 35 | Confined space entry procedure | 🔴 Critical |
| 36 | Lifting plan (AP) for all crane lifts | 🟡 Important |
| 37 | LTA abnormal load permits for crane/heavy transport | 🟡 Important |
| 38 | JTC Permit to Proceed (PTP) | 🔴 Critical |
| 39 | ASPRI Jurong Island HSSE induction for all workers | 🟡 Important |
| 40 | Lightning protection (FES only missing) | 🟡 Important |

### E. Commercial / Contractual

| # | Missing Item | Criticality |
| --- | --- | --- |
| 41 | Warranty / defects liability period (all vendors) | 🟡 Important |
| 42 | Liquidated damages clause (all vendors) | 🟡 Important |
| 43 | Performance bond (Credo waived; Synergex unstated) | 🟡 Important |
| 44 | Confirmed NaOH operating temperature & concentration | 🔴 Critical |
| 45 | O&M manual and spare parts list | 🟠 Recommended |

## SECTION 15 — VENDOR RANKING

### 15.1 Weighted Scorecard

| Criterion | Weight | FES | Credo | Synergex |
| --- | --- | --- | --- | --- |
| Price competitiveness | 20% | 10/10 | 3/10 | 3/10 |
| Technical scope completeness | 20% | 6/10 | 3/10 | 5/10 |
| API 650 compliance | 15% | 4/10 | 2/10 | 6/10 |
| NaOH service engineering | 10% | 3/10 | 2/10 | 3/10 |
| QA/Inspection provisions | 10% | 6/10 | 2/10 | 4/10 |
| Singapore regulatory compliance | 10% | 4/10 | 8/10 | 3/10 |
| Commercial accountability | 10% | 8/10 | 2/10 | 5/10 |
| Schedule certainty | 5% | 9/10 | 1/10 | 1/10 |
| WEIGHTED TOTAL | 100% | 6.15/10 | 2.95/10 | 4.10/10 |
| RANK |  | 1st | 3rd | 2nd |

### 15.2 Category Rankings

| Category | 1st | 2nd | 3rd |
| --- | --- | --- | --- |
| Best Technical Specification | Synergex | FES | Credo |
| Best Commercial Terms | FES | Synergex | Credo |
| Best Regulatory Coverage | Credo | FES | Synergex |
| Lowest Risk | FES | Synergex | Credo |
| Best Overall Value | FES | Synergex | Credo |

## SECTION 16 — FINAL RECOMMENDATION

### 16.1 Recommended Vendor: Falkor Engineering Services Pte Ltd (FES)

Recommended Contract Value: SGD 2,770,000 + 9% GST = SGD 3,019,300 all-in

Anticipated Variations (budgeted): SGD 150,000–300,000 (for RT/UT upgrade, bund redesign, passivation upgrade, height correction)

Total Budget Provision: SGD 3,200,000–3,320,000

Award Rationale:

Price advantage of SGD 1,298,000–1,330,000 vs. competitors (47–48% cheaper)

Only vendor with a firm 36-week project schedule

MDR, ITP, PSSR, hydrotest, calibration, and performance bond included

PE consultant (K P Koh & Partners) already identified and engaged

NDT contractor (SNDT), crane contractor (Denzai) already identified

ISO 9001, ISO 14001, OHSAS 18001 certified — structured QMS

Even with all scope gaps resolved as variations, FES remains the most economical option

Do NOT award to Credo (No LD, no bond, no hydrotest, undefined payment, broad exclusion clause — highest contractual risk)

Synergex is backup if FES cannot satisfy the mandatory conditions below.

### 16.2 Mandatory Pre-Award Conditions (All Must Be Resolved in Writing)

PO must not be issued until all 10 conditions below are satisfied in writing from FES.

| # | Condition | Deadline |
| --- | --- | --- |
| 1 | Revise NDT plan to include RT or UT for all vertical shell butt welds per API 650 §8.1. PT remains supplementary only. Confirm no price variation. | Before PO |
| 2 | Provide pile design calculation: type, diameter, length, working load/pile, FOS, geotechnical basis. 20 piles must be demonstrated as structurally adequate for 22,852 kN operating load. | Before PO |
| 3 | Revise tank height to minimum 15,840 mm (recommend 16,000 mm) to achieve ≥1,600 m³ working capacity with 300mm freeboard. Confirm revised price. | Before PO |
| 4 | Confirm and confirm in writing that full passivation per ASTM A380 (or citric acid equivalent) is included in scope, not only HF cleaning. | Before PO |
| 5 | Provide revised bund wall design demonstrating ≥1,760 m³ containment volume in compliance with NEA regulations. Address the 1,700mm foundation height in the containment calculation. | Before PO |
| 6 | Confirm explicit authority submissions included: JTC, BCA, SCDF, NEA, LTA(VP), URA, PUB, NParks. If any are excluded, confirm cost addition. | Before PO |
| 7 | Include lightning protection for both tanks. Confirm cost addition (estimate SGD 30,000–50,000 based on competitors). | Before PO |
| 8 | Confirm SAC-SINGLAS accreditation of SNDT for all applicable NDT methods. Provide SNDT accreditation certificate. | Before PO |
| 9 | Confirm CAR + PL insurance coverage limits. Confirm warranty/defects liability period (minimum 12 months from handover recommended). | Before PO |
| 10 | Client to provide NaOH operating concentration (% w/w) and temperature (min/max). FES to confirm SS304L is appropriate material for those conditions, or propose alternative if caustic SCC risk exists. | Before PO |

### 16.3 Pre-PO Actions Required from Client (CI Manufacturing)

Before issuing any PO to any vendor:

Issue formal Design Basis document stating: API 650 edition, NaOH concentration, operating temperature, design pressure/vacuum, corrosion allowance, wind speed, seismic zone, nozzle schedule, freeboard requirement, and bund containment volume.

Commission soil investigation (SI) for the Sakra Avenue tank farm location. Bore logs, SPT N-values, and consolidation data are essential to validate pile designs — especially FES's 20-pile design.

Obtain NEA hazardous substance storage license (NaOH) and confirm bund wall regulatory requirements with NEA before finalising civil design.

Appoint third-party inspection agency (TPI) for API 650 and welding surveillance. Budget SGD 25,000–40,000 separately.

Confirm NaOH concentration and operating temperature with process team. Commission caustic SCC risk assessment if operating temperature may exceed 40°C.

Re-issue RFQ with Design Basis to all three vendors to obtain like-for-like comparable bids before final award.

## APPENDIX A — SUMMARY SCORECARD

| Criterion | Weight | FES (Falkor) | Credo | Synergex |
| --- | --- | --- | --- | --- |
| Price | 20% | 10/10 | 3/10 | 3/10 |
| Technical scope | 20% | 6/10 | 3/10 | 5/10 |
| API 650 compliance | 15% | 4/10 | 2/10 | 6/10 |
| NaOH service engineering | 10% | 3/10 | 2/10 | 3/10 |
| QA/Inspection | 10% | 6/10 | 2/10 | 4/10 |
| Singapore regulatory | 10% | 4/10 | 8/10 | 3/10 |
| Commercial accountability | 10% | 8/10 | 2/10 | 5/10 |
| Schedule | 5% | 9/10 | 1/10 | 1/10 |
| WEIGHTED TOTAL |  | 6.15 — 1st | 2.95 — 3rd | 4.10 — 2nd |

## APPENDIX B — COMPLETE VENDOR QUESTIONS REGISTER

Questions to be sent to all three vendors before final evaluation:

Provide tank geometry (ID × shell height × overall height). Confirm working volume ≥1,600 m³ with stated freeboard.

State API 650 edition and list all applicable annexes.

State design wind speed (m/s) and basis (SS EN 1991-1-4 or equivalent).

State seismic design zone and method (API 650 Annex E).

State design temperature (minimum and maximum operating).

State design internal pressure and design external vacuum.

State corrosion allowance (mm) and technical justification.

State roof type and confirm design pressure.

Confirm top wind girder is included where H/D > 1.5.

Confirm bottom plate / annular plate design thickness.

Provide complete nozzle schedule (size, ANSI class, quantity, location).

Confirm internal sump, dip plate, anti-vortex plate, PV vent are included.

Confirm shell weld NDT method (RT or UT, not PT alone) and provide NDT plan.

Confirm vacuum box testing of bottom plate welds per API 650 §8.6 is included.

Confirm WPS/PQR and welder qualification (WPQ) records will be provided.

Confirm MTRs for all SS plates and fittings will be provided.

Confirm hydrostatic test to max design liquid level is included.

Confirm settlement monitoring survey post-hydrotest is included.

Confirm full passivation per ASTM A380 is included.

Confirm ITP and MDR/data book package will be provided.

Confirm as-built drawings will be issued at project completion.

State warranty period and defects liability terms.

Confirm NaOH operating temperature and concentration have been reviewed. Confirm SS304L is appropriate or propose alternative.

Confirm bund wall provides ≥1,760 m³ containment per NEA regulations.

Confirm all Singapore regulatory authority submissions are included (list all).

Provide pile design: type, diameter, length, working load/pile, FOS.

Confirm CAR + PL insurance coverage and limits.

Confirm performance bond will be provided.

State liquidated damages rate (per day or week of delay).

Provide reference projects: SS304L API 650 tanks in Singapore, last 5 years.

*Report prepared using: FES Quotation BC-Q3097/CIL/26 (4 Jun 2026), Credo Quotation CEC/CIL/011R2/26 (3 Jun 2026), Synergex Quotation SNG/006/01/26 R1 (29 May 2026), FES Engineering Drawings (4 Jun 2026), FES Project Schedule (4 Jun 2026), FES Technical Presentation — SS New Tank Erection 2 Nos (4 Jun 2026).*

*This report is for procurement decision support and does not constitute a PE-stamped engineering review. All structural, geotechnical, and process calculations must be verified by a Singapore-registered Professional Engineer before contract award. NaOH material compatibility must be confirmed by a qualified corrosion engineer.*